| CAMPBELL PROJECT MANAGEMENT TOOLKIT |  |
| --- | --- |

Work Breakdown Structure (WBS) Template

A practical project-planning tool that breaks a large project into smaller, assignable pieces of work so teams can estimate, schedule, own, and track delivery with less ambiguity.

| PROJECT / INITIATIVE | PROJECT OWNER | DATE |
| --- | --- | --- |

Easy Adoption Summary

| WHAT IT DOES | Breaks the project into a simple hierarchy of deliverables, work packages, and tasks. It makes the full scope visible before detailed scheduling begins. |
| --- | --- |
| WHO USES IT | Project manager, project owner, workstream leads, subject-matter experts, and the people responsible for estimating or delivering the work. |
| WHEN TO USE IT | Create it during project planning. Review it at kickoff and update it when approved scope changes occur. |
| HOW TO USE IT | Start with the final project outcome, list the major deliverables, break each deliverable into manageable work packages/tasks, assign one owner, add dates/dependencies, and confirm what “done” means. |

What is a Work Breakdown Structure?

A Work Breakdown Structure, or WBS, is a structured list of all the work required to deliver a project. It starts with the whole project and breaks it into smaller pieces until the work is clear enough to estimate, assign, schedule, and track. A WBS is not just a task list: it shows how each task connects to a larger deliverable and to the overall project outcome.

When is the WBS detailed enough?

Stop breaking work down when a task is small enough to estimate, assign to one accountable owner, place on a schedule, track during status reviews, and verify as complete. The goal is useful control - not unnecessary detail.

| CAMPBELL PROJECT MANAGEMENT TOOLKIT |  |
| --- | --- |

How the WBS Works

| # | STEP | WHAT TO DO |
| --- | --- | --- |
| 1 | Define the outcome | Write the project objective and the final result the organization must receive. |
| 2 | Identify major deliverables | List the major outputs or results required to achieve the project outcome. |
| 3 | Break deliverables into work packages | Divide each deliverable into smaller pieces that can be estimated, assigned, and monitored. |
| 4 | Add task controls | For each work package/task, identify an owner, dates, dependencies, status, and acceptance criteria. |
| 5 | Manage from the WBS | Use the WBS to build the schedule, assign work, review progress, and control approved scope changes. |

Simple WBS numbering

Use numbering to show the relationship between levels. Example: 1.0 = project, 1.1 = major deliverable, 1.1.1 = work package or task. Keep the numbering simple and consistent so the team can reference work quickly in meetings, schedules, and status reports.

Simple example

| WBS ID | LEVEL | DELIVERABLE / TASK | OWNER | DEPENDS ON |
| --- | --- | --- | --- | --- |
| 1.0 | Project | Strategic Plan Implementation | Project Manager | - |
| 1.1 | Major deliverable | Governance | Governance Lead | 1.0 |
| 1.1.1 | Work package | Update bylaws | Governance Lead | 1.1 |
| 1.1.2 | Work package | Approve committee structure | Board Chair | 1.1.1 |

Adoption tip: use the WBS as the single source for scope. New work should be added only when it is approved, assigned, and connected to the project structure.

| CAMPBELL PROJECT MANAGEMENT TOOLKIT |  |
| --- | --- |

Blank Work Breakdown Structure

Complete the table from top to bottom. Add rows as needed. Use one row for each deliverable, work package, or task. Suggested status values: Not Started | In Progress | At Risk | Blocked | Complete.

| PROJECT OBJECTIVE |  | PROJECT CADENCE | Example: weekly status review |
| --- | --- | --- | --- |
| SUCCESS / ACCEPTANCE CRITERIA |  | PROJECT SPONSOR |  |

WBS Detail

| WBS ID | DELIVERABLE / TASK | LEVEL | OWNER | START | DUE | DEPENDENCY | STATUS | DONE / ACCEPTANCE |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |